THREADCRAFT AI

Launch Checklist

From Zero to First Client

March 2026

Joey Rasmussen

# Launch Overview

This checklist covers everything needed to go from idea to operational business. Phases are sequential — complete each before moving to the next. Estimated total time to first client: 30–45 days.

## Phase 1: Legal & Business Identity

Get the entity, tax ID, and name locked down. Do this before opening any accounts.

|  | Task | Details | Timeline |
| --- | --- | --- | --- |
| ☐ | Get EIN from IRS.gov (Form SS-4 online) | Free, instant. Use SSN as responsible party. | Day 1 |
| ☐ | File DBA for "Threadcraft AI" with county clerk | Milwaukee County — typically $10–25 filing fee | Day 1–2 |
| ☐ | Register domain: threadcraft.ai | Cloudflare ($20–50/yr for .ai) or Namecheap | Day 1 |
| ☐ | Also grab threadcraftai.com as backup | $7–12/yr at any registrar | Day 1 |
| ☐ | Set up business email: joey@threadcraft.ai | Google Workspace ($7/mo) or Zoho (free tier) | Day 2 |
| ☐ | Choose business structure: Sole Prop for now | Revisit LLC/S-Corp when net income exceeds $40–50K | Day 1 |
| ☐ | NAICS code: 541511 or 541519 | Use on all applications and tax filings | Reference |
| ☐ | IRS business code for Schedule C: 541510 | Computer Systems Design and Related Services | Reference |

## Phase 2: Financial Foundation

Separate business and personal finances immediately. This protects you legally and makes tax time easier.

|  | Task | Details | Timeline |
| --- | --- | --- | --- |
| ☐ | Open business checking account | Chase, Mercury, or Relay. Bring EIN + DBA paperwork. | Day 3–5 |
| ☐ | Apply for Ink Business Unlimited credit card | 0% APR 12 months, 1.5% cash back, $0 annual fee | Day 5–7 |
| ☐ | Set up basic bookkeeping | Wave (free) or QuickBooks ($15/mo). Link bank + card. | Day 7–10 |
| ☐ | Set up quarterly estimated tax reminders | April 15, June 15, Sept 15, Jan 15. Mark calendar. | Day 7 |
| ☐ | Track all startup expenses from day 1 | Domain, hosting, API costs, tools — all deductible | Ongoing |

## Phase 3: Technical Infrastructure

Get your agent fleet and tooling production-ready.

|  | Task | Details | Timeline |
| --- | --- | --- | --- |
| ☐ | Stabilize OpenFang installation on Mac Mini M3 | Fix broken agents: clip-hand, browser-hand, collector-hand | Week 1–2 |
| ☐ | Configure OpenRouter for cloud API fallback | Claude, DeepSeek, Kimi. Set spending limits. | Week 1 |
| ☐ | Set up Tailscale for remote access | SSH from phone/laptop to Mac Mini anywhere | Week 1 |
| ☐ | Create agent workflow templates | Standardize: research, content, video, automation tasks | Week 2–3 |
| ☐ | Build QC pipeline (Gear agent) | Output validation, formatting checks, quality gates | Week 2–3 |
| ☐ | Set up project management system | Notion, Linear, or simple Kanban for client projects | Week 2 |
| ☐ | Set up client file delivery system | Google Drive shared folders or simple portal | Week 2 |

## Phase 4: Portfolio & Proof of Work

Nobody buys services without seeing examples. Build 3–5 demo projects before you pitch anyone.

|  | Task | Details | Timeline |
| --- | --- | --- | --- |
| ☐ | Complete 2 demo video packages | Breaking news style, 1080p, professional graphics | Week 2–3 |
| ☐ | Complete 1 automation workflow demo | Email sequence or data processing pipeline showcase | Week 2–3 |
| ☐ | Create 1 content batch sample | 5–10 social posts + blog post for a fictional brand | Week 3 |
| ☐ | Document each project as a case study | Problem, process, result, turnaround time, cost saved | Week 3–4 |
| ☐ | Record a 60-second screen capture walkthrough | Show agents working in parallel — the "wow" factor | Week 3–4 |

## Phase 5: Web Presence & Brand

Keep it simple. A one-page site with services, portfolio, and contact is enough to start.

|  | Task | Details | Timeline |
| --- | --- | --- | --- |
| ☐ | Build landing page at threadcraft.ai | Next.js or simple HTML. Services, portfolio, contact form. | Week 3–4 |
| ☐ | Set up social profiles | LinkedIn (priority), X/Twitter, GitHub if open-sourcing | Week 3 |
| ☐ | Create a simple logo | Canva, Looka, or AI-generated. Keep it clean and minimal. | Week 3 |
| ☐ | Write 2–3 LinkedIn posts about what you’re building | Show the agent fleet, share a demo, explain the concept | Week 3–4 |
| ☐ | Set up Google Business Profile | Helps with local Milwaukee visibility | Week 4 |

## Phase 6: First Clients

Leverage your existing network first. Cold outreach comes later.

|  | Task | Details | Timeline |
| --- | --- | --- | --- |
| ☐ | Pitch Boludo (Argentine restaurant) owner directly | Offer social content package as pilot. Discounted or free. | Week 4 |
| ☐ | Reach out to Grow414 prospects | You already have the agency infrastructure. Upsell AI. | Week 4–5 |
| ☐ | Offer one free pilot project to a local biz | Build a case study and testimonial in exchange | Week 4–5 |
| ☐ | Post in Milwaukee business / entrepreneur groups | Facebook, Reddit r/milwaukee, local Slack communities | Week 5–6 |
| ☐ | Ask for referrals from every satisfied pilot client | "Know anyone who could use this?" after every delivery | Ongoing |
| ☐ | Set up a simple proposal template | Services, timeline, deliverables, pricing. One-pager. | Week 4 |

## Phase 7: Ongoing Operations

Once clients are coming in, systemize everything so it scales.

|  | Task | Details | Timeline |
| --- | --- | --- | --- |
| ☐ | Create client onboarding checklist | Intake form, access credentials, brand guidelines, goals | Month 2 |
| ☐ | Build invoice template with Threadcraft AI branding | Wave, Stripe, or QuickBooks invoicing | Month 2 |
| ☐ | Set up contracts / service agreements | Simple template: scope, payment terms, IP ownership | Month 2 |
| ☐ | Track time per project for pricing validation | Toggl (free) or simple spreadsheet | Ongoing |
| ☐ | Monthly P&L review | Revenue minus API costs, tools, hosting = actual margin | Monthly |
| ☐ | Evaluate LLC / S-Corp election | When net SE income exceeds $40–50K, talk to a CPA | Month 6–12 |
| ☐ | Revisit credit card strategy | Add Ink Business Cash for 5% on telecom/internet | Month 6+ |

# Quick Reference

| Item | Details |
| --- | --- |
| Business Name (DBA) | Threadcraft AI |
| Primary Domain | threadcraft.ai |
| Backup Domain | threadcraftai.com |
| NAICS Code (Primary) | 541511 — Custom Computer Programming Services |
| NAICS Code (Alt) | 541519 — Other Computer Related Services |
| Schedule C Code | 541510 — Computer Systems Design |
| Entity Type | Sole Proprietorship (upgrade to LLC when justified) |
| Credit Card | Chase Ink Business Unlimited — 0% APR 12mo, 1.5% CB |
| Estimated Monthly Overhead | $350–$850 (APIs, hosting, tools) |
| Breakeven | 1–2 clients on any paid tier |
| Year 1 Target (Conservative) | $24K–$120K depending on client count |

Disclaimer

This checklist is for planning purposes. Consult a CPA for tax advice and an attorney for entity formation decisions specific to your situation. Revenue projections are estimates and not guaranteed.